## Slide 1
MICROSOFT PURVIEW
Data Management Maturity
Comprehensive Plan of Action
Module Linkages, Dependencies & Implementation Roadmap
Version 1.0 | March 2026

## Slide 2
Contents
01
Executive Summary & Core Principle
02
The Purview Ecosystem – Three Pillars
03
Master Dependency Map
04
Six-Phase Implementation Roadmap
05
Cross-Phase Dependency Matrix
06
RACI Model & Governance Roles
07
Maturity Assessment Framework
08
Risk Register & Quick Wins

## Slide 3
Executive Summary
Microsoft Purview unifies data governance, data security, and data compliance into a single management experience. Achieving maturity requires a carefully sequenced implementation where each module builds upon capabilities established before it.
CORE PRINCIPLE
You cannot protect what you cannot see, you cannot govern what you have not classified, and you cannot create business value from data that lacks business context.
Data Governance
Discover, classify & manage data across your estate
Data Security
Protect sensitive data with labels, DLP & DSPM
Data Compliance
Meet regulatory requirements & manage lifecycle

## Slide 4
The Purview Ecosystem – Three Pillars
DATA GOVERNANCE
Azure Purview
Data Map & Scanning
Unified Catalog
Glossary & Products
CDEs & OKRs
Data Quality
Lineage
DATA SECURITY
M365 Purview
Sensitivity Labels
DLP Policies
Insider Risk Mgmt
Adaptive Protection
DSPM & AI Obs.
Network Security
DATA COMPLIANCE
M365 Purview
Compliance Manager
Lifecycle Mgmt
Records Mgmt
eDiscovery & Audit
Comms Compliance
Privacy (Priva)
SHARED: Sensitivity Labels · Classifications · Lineage · Audit Logs · Purview Portal · Entra Integration
FOUNDATION: Data Map (Metadata Layer) — Everything Starts Here

## Slide 5
Master Dependency Map
Component | Depends On | Feeds Into | Why This Sequence
Data Map | — (Start) | Classifications, Catalog | No metadata = nothing to govern
Classifications | Data Map scans | Labels, DLP, Quality | Pattern detection for protection
Sensitivity Labels | Classifications | DLP, Insider Risk, Encryption | Labels carry classifications to action
Governance Domains | Data Map awareness | Glossary, Products, OKRs | Ownership boundaries scope governance
Enterprise Glossary | Gov. Domains | Products, Consumer discovery | Business context for technical data
Data Products | Map + Glossary + Domains | OKRs, Access, Quality rules | Bundled assets for consumption
CDEs | Products + Map columns | Quality rules, Standardisation | Unify synonyms across systems
Data Quality | Products, CDEs, Map | Health Controls, Trust | Validate data product reliability
DLP Policies | Labels, Classifications | DSPM, Compliance Mgr | Enforcement vehicle for protection
DSPM | DLP, Insider Risk, Labels | Exec dashboards, AI obs. | Unified posture consolidation
Compliance Manager | DLP, Labels, Retention | Regulatory reporting | Measures compliance posture

## Slide 6
Six-Phase Implementation Roadmap
PHASE 1
Data Map
Wk 1-6
Source Reg.
Scanning
Classification
Lineage
FOUNDATION
PHASE 2
Labels
Wk 4-10
Refine SITs
Label Taxonomy
Auto-Label
Encryption
PROTECTION
PHASE 3
Glossary
Wk 8-16
Gov. Domains
Glossary Terms
Asset Links
Roles
CONTEXT
PHASE 4
Products
Wk 14-22
Data Products
CDEs
Quality Rules
OKRs
VALUE
PHASE 5
Security
Wk 18-28
DLP
Insider Risk
DSPM
AI Obs.
ENFORCE
PHASE 6
Compliance
Wk 24-36+
Comp. Mgr
Lifecycle
Records
Health
SUSTAIN
Parallel Execution Windows
P1
P2
P3
P4
P5
P6

## Slide 7
P H A S E 1
Foundation – Data Map & Source Registration
"See everything before you govern anything"
Weeks 1–6
Key Activities
1. Provision Purview Enterprise instance & assign Data Governance Admin role
2. Inventory data sources across Azure, on-prem, AWS, Snowflake, Google Cloud, SaaS
3. Register & scan highest-value sources: Power BI, Azure SQL, ADLS Gen2
4. Configure scan levels (L1 metadata, L2 schema, L3 schema + classification)
5. Review scan outputs, validate classifications, assign initial asset owners
6. Establish platform domains (collections) in Data Map for technical grouping

## Slide 8
Phase 1 – Key Activities & Dependencies
Outputs & Deliverables
Populated Data Map with metadata from priority sources
Initial automated classifications applied
Scan schedules configured for freshness
Platform domain structure & ownership defined
Dependencies & Linkages
Feeds Phase 2: Scanned assets become input for labelling
Feeds Phase 3: Assets are raw material for domains & glossary
Feeds Phase 5: Asset visibility enables DLP scoping

## Slide 9
P H A S E 2
Classification, Labels & Info Protection
"Label what matters, protect what’s sensitive"
Weeks 4–10
Key Activities
1. Review & refine 300+ built-in SITs; create custom org-specific patterns
2. Design hierarchical label taxonomy (Public > Internal > Confidential > Highly Confidential)
3. Configure label actions: markings, encryption (Azure RMS), access restrictions
4. Deploy auto-labelling in simulation mode, then enforce after validation
5. Publish labels to pilot groups with training; extend to structured data

## Slide 10
Phase 2 – Key Activities & Dependencies
Outputs & Deliverables
Sensitivity label taxonomy deployed across M365
Auto-labelling running in simulation or enforcement
Custom SITs for org-specific patterns
Labels extended to structured data assets
Dependencies & Linkages
Feeds Phase 3: Glossary terms can carry label policies
Feeds Phase 5: DLP built on labels; no labels = blind DLP
Feeds Phase 6: Compliance Manager references label coverage

## Slide 11
P H A S E 3
Enterprise Glossary, Domains & Catalog
"Give data business meaning and ownership"
Weeks 8–16
Key Activities
1. Create 3-5 governance domains aligned to business functions
2. Assign domain owners, data stewards & data product owners
3. Build enterprise glossary from existing team vocabularies
4. Create catalog style guide for consistent term definitions
5. Link glossary terms to Data Map assets (bidirectional)
6. Publish initial glossary; grant catalog access to contributing teams

## Slide 12
Phase 3 – Key Activities & Dependencies
Outputs & Deliverables
Governance domains with ownership established
Enterprise glossary with linked assets published
Catalog style guide documented
Initial Unified Catalog access granted
Dependencies & Linkages
Requires Phase 1: Domains scoped against scanned assets
Requires Phase 2: Terms carry label-referenced policies
Into Phase 4: Glossary must exist before product curation

## Slide 13
P H A S E 4
Data Products, OKRs & Data Quality
"Package data for consumption"
Weeks 14–22
Key Activities
1. Create data products bundling assets under defined use cases
2. Link glossary terms to products for business discoverability
3. Define CDEs to group synonymous columns across systems
4. Deploy data quality rules using Data Quality scanner
5. Create OKRs linking governance to business outcomes
6. Configure self-service access with automated workflows
7. Endorse certified products; expand Catalog access

## Slide 14
Phase 4 – Key Activities & Dependencies
Outputs & Deliverables
Data products published with quality scores
CDEs standardising key entities across systems
OKRs connecting governance to business metrics
Self-service access workflows operational
Dependencies & Linkages
Requires Phase 1: Products built from Data Map assets
Requires Phase 3: Glossary & domains are prerequisites
Feeds Phase 5: Quality scores inform DSPM risk posture

## Slide 15
P H A S E 5
Data Security – DLP, Insider Risk & DSPM
"Enforce protection across the lifecycle"
Weeks 18–28
Key Activities
1. Deploy DLP policies using labels as conditions across M365
2. Extend DLP to endpoints and network (Shadow AI prevention)
3. Configure Insider Risk: data theft, leaks, Risky Agents for AI
4. Activate Adaptive Protection linking DLP to user risk scores
5. Set up DSPM consolidating DLP, Insider Risk & Info Protection
6. Enable AI observability for Copilot & third-party agents

## Slide 16
Phase 5 – Key Activities & Dependencies
Outputs & Deliverables
DLP enforcing across M365 and endpoints
Insider Risk detecting anomalous behaviours
DSPM dashboard with unified risk visibility
AI observability monitoring Copilot
Dependencies & Linkages
Requires Phase 2: DLP conditioned on sensitivity labels
Enriched by Phase 4: Quality & access patterns signal risk
Feeds Phase 6: DLP incidents feed Compliance Manager

## Slide 17
P H A S E 6
Compliance, Lifecycle & Continuous Improvement
"Close the loop and sustain maturity"
Weeks 24–36+
Key Activities
1. Configure Compliance Manager with GDPR, HIPAA, ISO 27001, SOX
2. Deploy retention policies using labels; configure disposition workflows
3. Establish records management file plan with regulatory locks
4. Activate Unified Catalog health controls; assign ownership
5. Deploy automated governance workflows for product publication
6. Export Purview Analytics to OneLake for Fabric analysis

## Slide 18
Phase 6 – Key Activities & Dependencies
Outputs & Deliverables
Compliance score baselined against frameworks
Retention & disposition automated
Health controls tracking maturity
Automated workflows replacing manual approvals
Dependencies & Linkages
Requires all phases: Full stack needed for compliance
Continuous: Health scoring drives improvement
Ongoing: Quarterly reviews as Purview evolves

## Slide 19
Enterprise Glossary – Connection Map
Enterprise Glossary
Active terms with policies
Phase 3
Data Map Assets
Phase 1
Sensitivity Labels
Phase 2
Governance Domains
Phase 3
Data Products
Phase 4
Data Consumers
All Phases
CDEs & Quality
Phase 4
INPUT
OUTPUT

## Slide 20
Cross-Phase Dependency Matrix
Phase | P1 Data Map | P2 Labels | P3 Glossary | P4 Products | P5 Security | P6 Compliance
P1: Data Map | — |  |  |  |  | 
P2: Labels | R | — |  |  |  | 
P3: Glossary | R | E | — |  |  | 
P4: Products | R | E | R | — |  | 
P5: Security | R | R | E | E | — | 
P6: Compliance | R | R | E | E | R | —
R = Required | E = Enriching

## Slide 21
RACI Model for Data Governance Roles
Activity | Responsible | Accountable | Consulted | Informed
Data Map registration | Data Owner | Gov Admin | IT/Platform | Data Office
Classification review | Data Steward | Gov Admin | Data Owner | Consumers
Label design | Data Office | CISO/DPO | IT Security | Data Owners
Governance domains | Data Office | Gov Admin | Domain Owners | All users
Glossary curation | Data Steward | Domain Owner | Consumers | Data Office
Data products | Product Owner | Domain Owner | Data Steward | Consumers
DLP deployment | IT Security | CISO | Data Office | Data Owners
DSPM dashboard | IT Security | CISO | Gov Admin | Exec Sponsors
Compliance reviews | Compliance | DPO/CISO | Data Office | Exec Sponsors
OKR tracking | Biz Strategy | Domain Owner | Data Steward | Exec Sponsors

## Slide 22
Maturity Assessment Framework
1
Ad Hoc
No inventory
Reactive
2
Managed
Data Map
Labels active
P1-P2
3
Defined
Glossary live
Products curated
P3-P4
4
Measured
DLP enforcing
DSPM active
P5
5
Optimised
Full suite
AI governance
P6+
← Lower Maturity Higher Maturity →

## Slide 23
Risk Register & Mitigation
Risk | L | I | Mitigation
Insufficient scan coverage | M | H | Start with highest-value sources; quarterly review
Glossary terms unused | H | M | Mandate linking to products before publication
Poor catalog trust | M | H | Quality rules before broad access
DLP false positives | H | M | Simulation mode first; tune before enforcement
Licensing gaps | M | H | Pre-assess E3/E5/add-on mapping
Org resistance | H | H | Executive sponsorship; start where stewardship exists
Domain misalignment | M | M | Document platform vs governance domain distinction
AI governance gaps | M | H | Prioritise DSPM if Copilot deployed

## Slide 24
Timeline & Quick Wins
Phase | Duration | Parallel Opportunity | Key Milestone
P1: Data Map | Wk 1-6 | Begin P2 Wk 4 | Map with tier-1 sources
P2: Labels | Wk 4-10 | Begin P3 Wk 8 | Auto-labelling in simulation
P3: Glossary | Wk 8-16 | Begin P4 Wk 14 | Terms published & linked
P4: Products | Wk 14-22 | Begin P5 Wk 18 | Products with quality scores
P5: Security | Wk 18-28 | Begin P6 Wk 24 | DLP enforcing; DSPM active
P6: Maturity | Wk 24-36+ | Continuous improvement | Compliance score baselined
Quick Wins – First 30 Days
Week 1
Create Purview account, assign Gov Admin, register Power BI + primary SQL
Week 2
Run first scans, review classifications, add owners to top 10 assets
Week 3
Create first governance domain; assign initial stewards
Week 4
Draft label taxonomy; begin auto-labelling simulation

## Slide 25
Closing the Classification Gap – Custom Connector Strategy
Addressing Purview’s native scanning limitations for SaaS sources
THE LIMITATION
Purview’s native Salesforce, NetSuite, and Workday connectors extract metadata (objects, fields, schemas) but do not support automated data classification (no L3 scan). Salesforce does not appear as a source type in custom scan rule sets. This is confirmed platform behaviour, not a configuration issue.
THE SOLUTION
Custom Python connectors bypass the native scanner entirely. They pull metadata directly from each source’s REST API, then push classifications, lineage, and business metadata into Purview via the Atlas v2 API. The result in the Unified Catalog is indistinguishable from a native L3 scan.
Connector | Source System | Auth Method | What It Pushes to Purview
purview_salesforce_connector.py | Salesforce CRM | OAuth 2.0 | Objects, fields, classifications, cross-system lineage, business metadata
purview_netsuite_connector.py | Oracle NetSuite | OAuth 1.0a (TBA) | Record types, fields, classifications, lineage to DW/BI
purview_workday_connector.py | Workday HCM | OAuth 2.0 + refresh | Business objects, fields, PII classifications, lineage to AD
purview_sql_connector.py | SQL Server | Service Principal | DB → schema → table → column hierarchy, lineage, business metadata
How It Works
1. Source API
Connector authenticates to SaaS source and discovers all objects, fields & schemas
2. Classify
Applies built-in + custom classifications programmatically (PII, financial, health data)
3. Push to Purview
Creates entities, lineage & metadata via Atlas v2 API into Data Map
4. Catalog Ready
Assets appear in Unified Catalog with full classifications — identical to native L3 scan

## Slide 26
DAMA DMBOK2 Alignment
Mapping the DAMA Data Management Body of Knowledge
to Microsoft Purview Modules & Our Implementation Phases
Framework: DAMA-DMBOK2R, DAMA International, 2024

## Slide 27
DAMA DMBOK2 → Purview Module Mapping
Every DAMA knowledge area mapped to a specific Purview capability and roadmap phase
DAMA Knowledge Area | Microsoft Purview Module | Roadmap Phase | Coverage
Data Governance (Hub) | Unified Catalog, Governance Domains, Health Controls | P3, P6 | Full
Data Architecture | Data Map (source registration, collections, platform domains) | P1 | Partial
Data Modeling & Design | Data Map (schema capture), Lineage visualisation | P1 | Partial
Data Storage & Operations | Data Map (native + custom connectors: Azure, AWS, GCP, Salesforce, NetSuite, Workday) | P1 | Moderate
Data Security | Info Protection, DLP, Insider Risk, DSPM, Adaptive Protection | P2, P5 | Full
Data Integration & Interoperability | Data Map (lineage) + Custom connectors (cross-system lineage via Atlas v2) | P1, P4 | Full
Document & Content Mgmt | Sensitivity Labels on M365 (SharePoint, OneDrive, Teams) | P2, P6 | Moderate
Reference & Master Data | Critical Data Elements (CDEs), Data Products | P4 | Moderate
Data Warehousing & BI | Data Map (Power BI, Fabric connectors), Purview Analytics to OneLake | P1, P6 | Moderate
Metadata Management | Data Map + Custom connectors (SaaS metadata) + Enterprise Glossary | P1, P3 | Full
Data Quality | Data Quality scanner, Health Controls, CDE quality rules | P4, P6 | Full
Coverage: Full = Purview (native + custom connectors) provides comprehensive capability | Moderate = Purview covers key aspects; custom connectors extend reach | Partial = Purview contributes metadata visibility; dedicated design tools needed

## Slide 28
DAMA Wheel → Purview: Where Each Area Lands
FULL COVERAGE – Purview native + custom connectors
Data Governance
Unified Catalog, Domains, Health Controls
P3 + P6
Data Security
DLP, Insider Risk, DSPM, Labels
P2 + P5
Metadata Management
Data Map + Custom Connectors + Glossary
P1 + P3
Data Quality
Quality Scanner, CDEs, Health Controls
P4 + P6
Data Integration
Custom connectors: cross-system lineage via Atlas v2
P1 + P4
MODERATE COVERAGE – Purview covers key aspects; custom connectors extend reach
Data Storage & Ops
Native + custom connectors for SaaS sources
P1
Document & Content
Sensitivity Labels on M365
P2 + P6
Reference & Master Data
CDEs + Data Products
P4
DW & BI
Power BI / Fabric connectors
P1 + P6
PARTIAL – Metadata visibility only; dedicated design tooling needed
Data Architecture
Data Map source registration & collections
P1
Data Modeling & Design
Schema capture & lineage visualisation
P1
Remaining Gaps: Custom connectors have closed the SaaS classification and lineage gaps (Salesforce, NetSuite, Workday). Data Architecture and Data Modeling remain the only areas where Purview provides metadata visibility but not design tooling. Pair with dedicated tools (e.g., erwin, ER/Studio) for complete DAMA coverage.
Framework: DAMA-DMBOK2R, DAMA International, 2024. Diagram © 2024 DAMA International.

## Slide 29
Best Practices
Key Recommendations from the Data Governance Handbook
Wendy S. Batchelder (Packt, 2024)
Integrated into our Microsoft Purview roadmap

## Slide 30
Treat Data as Both Asset and Liability
Batchelder Ch.1 – Applied to Phase 1 (Data Map)
DATA AS ASSET – Creates Value
Curated datasets used for multiple purposes
Customer health scoring models
Authorised provisioning points (golden sources)
Predictive models from trusted data
Purview Action: Endorse Data Products in Unified Catalog to signal certified, reusable assets.
DATA AS LIABILITY – Creates Risk
Non-catalogued data with no known owner
Data used for decisions it was never intended for
Security risk from not knowing where data resides
Unmanaged data = higher liability, not more data
Purview Action: Use Data Map scanning + DSPM to surface uncatalogued, unprotected data liabilities.
Key Principle: "Data equity increases through delivery. Momentum created by delivery should translate directly to an increase in data equity over time." – Batchelder

## Slide 31
Build a Coalition of Advocates Before You Launch
Batchelder Ch.2 – Applied Across All Phases
1
Land an Executive Sponsor
Identify someone with authority, funding, and a vested interest in data outcomes. Without sponsorship, governance becomes a cost centre.
Map to Purview: Sponsor must approve Data Governance Admin role assignment (Phase 1).
2
Build a Stakeholder Map
Identify primary, secondary, and tertiary stakeholders. Understand their pain points through listening sessions, not presentations.
Map to Purview: Stakeholder map informs governance domain ownership (Phase 3).
3
Focus on Trust, Not Culture
Batchelder argues "data culture" programmes often fail. Instead, focus on building trust in data through transparent, reliable delivery.
Map to Purview: Data Quality scoring + Endorsed products = trust signals (Phase 4).
4
Translate to Business Outcomes
Governance fails when framed in data terms. Reframe every capability in terms of revenue, cost savings, or risk reduction.
Map to Purview: OKRs in Unified Catalog connect governance directly to business goals (Phase 4).

## Slide 32
Baseline Before You Build – Maturity Assessment
Batchelder Ch.4 – Applied to Phase 1 & Ongoing
Batchelder’s 10-step maturity assessment process, mapped to our Purview phases:
Step | What It Means | Purview Mapping
1. Define scope | Determine which data domains, systems & divisions to assess | Phase 1: Align with Data Map source registration scope
2. Identify stakeholders | Use RACI – responsible, accountable, consulted, informed | Phase 1: Governance Admin + domain executives
3. Select maturity model | DCAM, CMMI-DMM, or custom – use established model first | Aligns to our Level 1-5 Maturity Framework (Section 7)
4. Execute assessment | Workshops preferred over self-scoring to prevent gaming | Pre-Phase 1: Run before Purview deployment begins
5. Analyse data | Quantitative scores + qualitative themes from listening | Informs which Purview phases to prioritise
6. Communicate results | Aggregated enterprise score first; disaggregate later | Present to Enterprise Data Committee
7. Develop a plan | Prioritise common themes that benefit the whole org | This roadmap is the plan – adapt phase timelines to baseline
8. Implement the plan | Follow the six-phase Purview roadmap | Phases 1-6 with parallel execution windows
9. Monitor progress | Track via Health Controls in Unified Catalog | Phase 6: Ongoing health scoring
10. Reassess maturity | Annual reassessment to measure improvement | Annual: Compare against original baseline

## Slide 33
Quick Wins & Continuous Delivery Model
Batchelder Ch.13 – Applied Across Phases 1-4
Key Insight: "Data leaders who bet exclusively on big transformational platforms often lose stakeholder interest by the time results are realised. Shorten time to first value." – Batchelder
1. Intake
Collect issues from stakeholder listening sessions. Document everything.
2. Prioritise
Score by impact (H/M/L) and effort. Focus on high-impact, low-effort first.
3. Build MVP
Deliver minimum viable product. Apply product mindset to data capabilities.
4. Demo & Iterate
Show stakeholders early. Get feedback. Don’t wait until it’s perfect.
5. Go Live
Turn on with urgency. Continue delivering features post-launch.
6. Communicate
Share wins broadly. Quantify impact: time saved, revenue found, risk reduced.

## Slide 34
Metadata, Glossary & Building Trust in Data
Batchelder Ch.6-8 – Applied to Phases 1, 3, 4
Business Glossary Best Practices
Start with terms teams already use – don’t invent new vocabulary
Publish a quick reference guide of basic terms accessible to the whole org
Measure: terms defined / total terms; terms with assigned owners / total terms
Glossary drives clarity, reusability, and is the foundation for all subsequent capabilities
Purview: Build glossary terms in Unified Catalog (Phase 3) before creating Data Products (Phase 4).
Data Catalog & Marketplace Vision
A catalog should answer: What data do we have? Who owns it? How is it classified? Can I trust it?
Batchelder envisions a ‘Data Marketplace’ combining glossary, catalog, lineage, quality & certified assets
Measure value by employee time saved – analysts spend 50%+ of time searching for data
Certified vs. non-certified: CDAO stands behind certified assets only
Purview: Unified Catalog IS the data marketplace. Combine Data Map + Glossary + Products + Quality.
Data Quality as Trust Currency
Quality is like exercise: you can’t get in shape once and stop. It requires ongoing maintenance
Define quality rules for each Critical Data Element (CDE) and monitor continuously
Measure value in business terms: revenue impact, cost of poor decisions, fine avoidance
Transparency is key – provide quality dashboards so stakeholders can see trust levels themselves
Purview: Deploy Data Quality scanner on CDEs (Phase 4). Health Controls track ongoing fitness (Phase 6).

## Slide 35
Adoption & Governance by Design
Batchelder Ch.14-16 – Applied to Phase 6 & Ongoing
Governance must be embedded into process, not bolted on. Batchelder calls this “governance by design.”
Why Adoption Fails
The solution is the problem – too complex, not user-friendly
The company is the problem – competing priorities, no exec support
You are the problem – failing to communicate value in business terms
Low adoption is costly: wasted investment, eroded trust, loss of future funding
How to Succeed
Start with why – connect every feature to a user need
Make it easy to use – simplify the experience ruthlessly
Bake adoption into SDLC – governance as part of the build process, not after
Monitor post-deployment: track active users, feature usage, feedback loops
Governance by Design in Purview
Auto-labelling embeds classification into document creation (Phase 2)
Glossary terms carry active policies that flow to data products (Phase 3)
Access request workflows replace ad-hoc provisioning (Phase 4)
DSPM + Adaptive Protection auto-adjusts security posture (Phase 5)

## Slide 36
Thank You
This plan should be reviewed quarterly and updated as Microsoft Purview capabilities evolve and your organisation’s maturity advances through each phase.
Version 1.0 | March 2026 | CONFIDENTIAL